KTS ENTERPRISE  /  PEOPLE & OPERATIONS

# Operations Manager

Seven Day Training Module

A practical onboarding program for coordinating KTS Academy operations and KTS Digital Solutions delivery, with hotels as the priority client segment.

| PROGRAM LENGTH | DAILY FORMAT | FINAL OUTCOME |
| --- | --- | --- |
| 7 working days | 6 guided hours per day, plus a 15-minute close | A live-ready operating plan and hotel project capstone |

## How to use this module

The trainer should demonstrate each process, let the Operations Manager practice it in the shared KTS workspace, then review the day’s evidence together. Use training records or clearly marked sample records until the manager is authorized to handle live company or client data.

Training principle The Operations Manager owns visibility, follow-through, and escalation. Functional specialists remain accountable for technical decisions and specialist work.

## Role outcomes

Run a dependable weekly and daily operating rhythm across KTS ventures.

Turn approved hotel opportunities into scoped, scheduled, tracked delivery work.

Use one shared KTS workspace and database with role-appropriate access.

Keep owners, dates, decisions, risks, evidence, and next actions visible.

Escalate early, protect client and student information, and close work cleanly.

# Program at a glance

| DAY | FOCUS | END OF DAY EVIDENCE |
| --- | --- | --- |
| 1 | KTS context, role, access, and operating cadence | Role map, access check, daily control board |
| 2 | KTS Academy and cross-venture operations | Sample daily report and issue escalation |
| 3 | Digital project delivery from intake to handover | Project charter, checklist, owner and milestone plan |
| 4 | Hotel client journey and service readiness | Hotel discovery brief, proposal handoff, follow-up plan |
| 5 | People coordination, quality, risk, and capacity | RACI, risk log, capacity review, QA gates |
| 6 | Reporting, communication, records, and data care | Weekly dashboard review and concise status update |
| 7 | Capstone simulation and readiness decision | End-to-end hotel project simulation and 30-day plan |

## Daily learning cycle

| TIME | ACTIVITY | METHOD |
| --- | --- | --- |
| 09:30–10:00 | Check-in and recall | Review yesterday’s evidence and answer open questions. |
| 10:00–11:15 | Learn and observe | Trainer explains the workflow and models a good example. |
| 11:15–12:30 | Guided practice | Trainee completes a realistic task with coaching. |
| 13:15–14:45 | Independent practice | Trainee repeats the task using a new scenario. |
| 14:45–15:15 | Review and feedback | Compare work with the day’s quality standard. |
| 15:15–15:30 | Close and commit | Record evidence, blockers, and tomorrow’s preparation. |

The trainer may adjust the clock for KTS business hours. Keep the practice, feedback, and evidence review even if the schedule shifts.

# Day 1  KTS context and the Operations Manager role

LEARNING GOAL

Understand how KTS ventures work together, what the Operations Manager owns, how decisions are made, and how to enter the shared workspace safely.

## Core topics

KTS Enterprise structure: KTS Academy, education and skills activity, and KTS Digital Solutions.

Role boundaries: coordinate and unblock; do not approve technical scope, pricing, or client commitments without delegated authority.

Shared dashboard orientation: overview, Academy operations, Digital projects, hotel sales pipeline, and role workspaces.

Access basics: sign in with the provisioned employee account, confirm role-based access, sign out on shared devices.

Operating cadence: daily check-in, weekly review, monthly improvement discussion.

## Suggested session plan

| TIME | SESSION |
| --- | --- |
| 09:30 | Welcome, expectations, and baseline self-assessment |
| 10:00 | KTS ventures, customers, services, and hotel priority |
| 11:15 | Role map, decision rights, and escalation paths |
| 13:15 | Guided tour of the employee portal and shared dashboard |
| 14:15 | Set up a sample daily board: owner, due date, status, blocker, next action |
| 15:00 | Review access and agree personal learning goals |

## Hands-on exercise

Using sample records, identify three tasks that belong to Operations, three decisions that require an owner or specialist, and two items that require escalation. Create a one-day operating board with owners and next actions.

Evidence to review A completed role and escalation map; a working sample daily board; confirmed sign-in and access to only the assigned workspace.

Trainer checkpoint Can the trainee explain who owns delivery, how work is recorded, and whom to contact when blocked?

# Day 2  KTS Academy and cross-venture operations

LEARNING GOAL

Coordinate recurring Academy activities while applying the same clear ownership and issue tracking used across KTS.

## Core topics

Opening readiness: rooms, timetable, faculty attendance, equipment, and planned substitutions.

Class and batch coordination: schedule changes, attendance exceptions, and communication ownership.

Tests and CBT: readiness checklist, issue log, incident escalation, and post-test closeout.

Student follow-up: use approved identifiers and store only details necessary for the operational action.

Facilities, complaints, and daily reports: classify, assign, set a target date, and confirm resolution.

## Suggested session plan

| TIME | SESSION |
| --- | --- |
| 09:30 | Review a sample Academy daily report |
| 10:00 | Map the daily operating rhythm from opening through close |
| 11:15 | Practice a timetable change and faculty substitution scenario |
| 13:15 | Run a sample test-readiness and issue-escalation exercise |
| 14:15 | Create a facility issue and student follow-up task using minimal data |
| 15:00 | Write a concise end-of-day report |

## Hands-on exercise

A faculty member is absent, a classroom projector fails, and a test begins in 45 minutes. Prioritize actions, assign owners, record the issue, send the right updates, and close the loop after resolution.

Evidence to review A sample daily Academy report with staffing, schedule, test readiness, open issues, owners, and next-day actions.

Trainer checkpoint Are urgent learning disruptions escalated immediately, assigned to a named owner, and tracked until confirmed resolved?

# Day 3  Digital project delivery controls

LEARNING GOAL

Coordinate a Digital Solutions project through approved intake, planning, build, quality checks, launch, and handover.

## Core topics

Intake gate: client goals, users, current systems, constraints, success measures, and decision makers.

Scope control: written deliverables, exclusions, assumptions, acceptance criteria, approvals, and change requests.

Project setup: project owner, specialist owners, milestones, due dates, dependencies, client touchpoints, and evidence location.

Delivery phases: discovery, design, build/configuration, QA, client review, launch, training, support, and closeout.

Issue management: impact, urgency, owner, mitigation, client communication, decision needed, and escalation date.

## Suggested session plan

| TIME | SESSION |
| --- | --- |
| 09:30 | Review the project checklist and sample project record |
| 10:00 | Turn a client request into goals and acceptance criteria |
| 11:15 | Build milestones, dependencies, owners, and client review points |
| 13:15 | Run a blocked-task and change-request simulation |
| 14:15 | Practice QA, launch approval, and handover checks |
| 15:00 | Review project health and identify schedule risk |

## Hands-on exercise

Create a sample project for a hotel website refresh. Include approved scope, milestones, accountable owners, one dependency, a review cycle, QA evidence, launch approval, training, and support handover. Mark assumptions clearly; do not invent approved pricing.

Evidence to review A project charter and populated delivery checklist with no unowned critical tasks and clear acceptance evidence.

Trainer checkpoint Can the trainee detect scope drift, a missed dependency, or an overdue milestone and get a decision before the deadline is at risk?

# Day 4  Hotel client journey and service readiness

LEARNING GOAL

Coordinate a respectful, consistent hotel client journey from prospect qualification through discovery and delivery handoff.

## Core topics

Hotel prospect record: property and contact, source, need, room or property scale where relevant, current systems, owner, stage, and next follow-up date.

Discovery: business goal, guest journey, booking path, brand, local search, content, analytics, integrations, approvals, and constraints.

Service fit: website and landing pages, digital marketing, local visibility, content, lead generation, analytics, or technology work only where KTS can deliver.

Sales-to-delivery handoff: confirmed problem, agreed scope, decision maker, approval status, commercial terms, commitments, and open questions.

Client communication: one named KTS contact, meeting notes, clear next step and date, and no unsupported guarantees.

## Suggested session plan

| TIME | SESSION |
| --- | --- |
| 09:30 | Review hotel lead stages and follow-up discipline |
| 10:00 | Practice hotel discovery questions and active listening |
| 11:15 | Map a hotel guest journey and identify measurable opportunities |
| 13:15 | Qualify a sample opportunity and record missing information |
| 14:15 | Prepare a sales-to-delivery handoff for a hypothetical approved project |
| 15:00 | Role-play a client update and a delayed response |

## Hands-on exercise

A boutique hotel requests “more bookings” and a new website. Conduct a mock discovery, capture the booking path and current tools, record success measures and constraints, and produce a handoff. Leave unconfirmed budget, integration feasibility, and timing as open questions.

Evidence to review A hotel discovery brief, qualified lead record with dated next action, and a handoff that separates confirmed facts from questions.

Trainer checkpoint Does every active hotel lead have a stage, an owner, a dated next action, and a clear reason the opportunity fits KTS?

# Day 5  Team coordination, quality, risk, and capacity

LEARNING GOAL

Keep work balanced and dependable by clarifying responsibilities, checking quality gates, managing risks, and escalating decisions.

## Core topics

Responsibility mapping: accountable owner, responsible specialist, consulted parties, and informed stakeholders.

Capacity planning: active work, effort estimates from owners, absences, priority conflicts, and realistic commitments.

Quality gates: requirements review, design approval, functional checks, content and link checks, analytics, backup or recovery readiness, client acceptance, and handover.

Risk and issue log: likelihood, impact, trigger, mitigation, owner, due date, and escalation threshold.

Decision log and change control: what changed, who approved it, when it takes effect, and any impact on scope, cost, schedule, or quality.

## Suggested session plan

| TIME | SESSION |
| --- | --- |
| 09:30 | Review current sample workload and owners |
| 10:00 | Build a responsibility map for hotel project delivery |
| 11:15 | Run a capacity conflict and reprioritization exercise |
| 13:15 | Score sample delivery risks and define triggers |
| 14:15 | Use a quality gate and change request scenario |
| 15:00 | Practice an escalation briefing with options and recommendation |

## Hands-on exercise

Two projects need the same developer before a client review. One has an external launch date; the other has a flexible internal deadline. Gather facts, ask owners for estimates, surface tradeoffs, propose options, and escalate for a decision rather than silently reprioritizing.

Evidence to review A responsibility map, current capacity view, risk log with owners and trigger dates, and one documented decision or change request.

Trainer checkpoint Does the trainee raise risks early with impact, evidence, a named owner, and a decision deadline?

# Day 6  Reporting, communication, and information care

LEARNING GOAL

Produce accurate operating updates from the shared KTS records and communicate progress without exposing unnecessary personal or client information.

## Core topics

Dashboard hygiene: current status, due dates, owners, blockers, next actions, and recent updates.

Weekly review: completed work, upcoming milestones, overdue items, risks, hotel lead movement, Academy exceptions, decisions required, and capacity.

Status writing: concise summary, facts, impact, action owner, due date, and decision request.

Information care: minimum necessary details, approved access, secure account use, and careful handling of student and hotel client data.

Record discipline: timely updates, consistent names and stages, evidence of approval, and closeout notes.

## Suggested session plan

| TIME | SESSION |
| --- | --- |
| 09:30 | Review sample records for completeness and accuracy |
| 10:00 | Build a weekly operating review from the dashboard |
| 11:15 | Separate facts, risks, assumptions, and decisions needed |
| 13:15 | Practice writing an owner-ready update and escalation |
| 14:15 | Review data minimization and account-access scenarios |
| 15:00 | Conduct a mock 20-minute weekly review |

## Hands-on exercise

Using a prepared sample dashboard, write a one-page weekly summary that names the three most important delivery risks, hotel follow-ups due next week, Academy exceptions, owners, dates, and decisions needed. Remove unnecessary personal details.

Evidence to review A weekly review pack, concise escalation message, and updated sample records with source evidence and next actions.

Trainer checkpoint Can another KTS manager understand the work status and act without chasing the trainee for basic facts?

# Day 7  Capstone and readiness review

LEARNING GOAL

Demonstrate end-to-end operating judgment across a hotel opportunity, delivery plan, cross-functional work, reporting, and escalation.

## Core topics

Review the operating standards and open learning questions.

Capstone scenario: qualify a hotel request, record it, establish the handoff, create the project plan, manage a blocker, report status, and define closeout.

Trainer observation: accuracy, prioritization, communication, system use, data care, and role boundaries.

Readiness conversation: strengths, support needed, delegated authority, and first-month outcomes.

## Suggested session plan

| TIME | SESSION |
| --- | --- |
| 09:30 | Knowledge check and capstone briefing |
| 10:00 | Hotel discovery and lead qualification simulation |
| 11:15 | Approved opportunity handoff and project setup |
| 13:15 | Handle scope change, capacity risk, and client update injects |
| 14:15 | Present dashboard status and closeout plan |
| 15:00 | Scorecard review and 30-day commitments |

## Hands-on exercise

Capstone: A hotel approves a website and local visibility project after discovery. Midway through, the client requests a booking-system integration not in the approved scope; the assigned specialist reports a dependency risk; the client review is in four days. The trainee must record facts, protect scope, get specialist input, present options to the authorized decision maker, set an owner and date, and communicate a clear client update.

Evidence to review Completed capstone records, a short management briefing, and a 30-day development plan agreed with the manager.

Trainer checkpoint Ready only when access, follow-through, escalation, communication, quality, and information-care standards meet the pass criteria below.

# Readiness assessment

Score each area from 1 to 4 using observed work from the capstone. A score of 3 means the trainee can perform the task independently to the KTS standard. Record specific evidence and any support required.

| AREA | 1 NEEDS CLOSE SUPPORT | 2 DEVELOPING | 3 READY | SCORE |
| --- | --- | --- | --- | --- |
| Dashboard and records | Cannot keep essential fields current | Needs reminders to update | Records are accurate, owned, and current | ___ / 4 |
| Prioritization | Misses urgency or impact | Recognizes issues with prompts | Prioritizes by impact, deadline, and dependency | ___ / 4 |
| Project control | Scope, owners, or dates are unclear | Plan needs regular correction | Tracks scope, milestones, quality, and handover | ___ / 4 |
| Hotel client coordination | Follow-ups or commitments are unclear | Communicates with coaching | Clear, timely, accurate updates and dated next steps | ___ / 4 |
| Escalation and judgment | Delays or bypasses decisions | Escalates but lacks options or context | Escalates early with impact, options, owner, and deadline | ___ / 4 |
| Information care | Uses unnecessary sensitive details | Needs reminders on access and data minimization | Uses approved access and minimum necessary data | ___ / 4 |
| Team coordination | Owners or handoffs are missed | Coordinates with frequent prompts | Confirms owners, dependencies, and completion evidence | ___ / 4 |

## Pass standard

At least 21 of 28 points overall.

A score of 3 or higher in escalation and judgment, information care, and dashboard and records.

No unresolved critical error involving unauthorized client commitments, access misuse, or avoidable disclosure of personal information.

Any unmet criterion receives a named support owner and a dated reassessment.

| RESULT | SELECT ONE |
| --- | --- |
| Ready for delegated Operations Manager responsibilities | ☐ |
| Ready with a defined support plan | ☐ |
| Additional supervised practice required | ☐ |

Trainer name: ______________________________    Trainee: ______________________________

Review date: _______________________________    Next check-in: _________________________

## First 30 days after training

| PERIOD | FOCUS | MANAGER CHECK-IN |
| --- | --- | --- |
| Week 1 | Run the daily board and maintain owners, due dates, and blockers. | Review daily for 15 minutes. |
| Week 2 | Own one Academy operating cycle and one hotel lead follow-up rhythm. | Review exceptions and client follow-through. |
| Week 3 | Coordinate one active Digital project through a quality or client review gate. | Review scope, risk, and capacity decisions. |
| Week 4 | Present a weekly operating review and improvement recommendation. | Confirm delegated authority and next development goal. |

## Trainer preparation checklist

Confirm the trainee’s Firebase employee account and approved role before training.

Prepare sample-only Academy, hotel lead, and project records; do not expose live client or student data during practice.

Identify the decision maker for scope, pricing, launch approval, and priority conflicts.

Gather current KTS service descriptions, escalation contacts, templates, and approved communication channels.

Reserve daily review time and score observed evidence rather than attendance alone.

Role access in the current KTS workspace: enterprise_owner and operations_manager can access Academy operations, Digital projects, hotel leads, and overview. Dashboard access does not itself grant authority to make commercial or technical decisions.